## TASK
task_code | status_code | wbs_id | task_name | act_start_date | act_end_date | resource_list | delete_record_flag | From TimeControl
Activity ID | Activity Status | WBS Code | Activity Name | Actual Start | Actual Finish | (*)Resources | Delete This Row | Project | Project Desc | Charge Code | Charge Description | End Date | Status | Start Date | Resource | Resource Description | Date Work Performed | Hours
POLAR.6 | Unopened | POLAR.6 | Product Launch | 10/09/2012 8:00:00 AM | 10/12/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.6 | Product Launch | Unopened | 20121009 | 20121012 | Non Billable | R and D Non Eligible | Non Capitizable
POLAR.5 | Unopened | POLAR.5 | Marketing | 09/25/2012 8:00:00 AM | 10/09/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.5 | Marketing | Unopened | 20120925 | 20121009 | Non Billable | R and D Non Eligible | Capitalizable
POLAR.4.3 | Unopened | POLAR.4.3 | Training Materials | 10/18/2012 8:00:00 AM | 11/08/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.4.3 | Training Materials | Unopened | 20121018 | 20121108 | Non Billable | R and D Non Eligible | Capitalizable
POLAR.4.2 | Unopened | POLAR.4.2 | Reference Docs | 10/02/2012 8:00:00 AM | 10/18/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.4.2 | Reference Docs | Unopened | 20121002 | 20121018 | Non Billable | R and D Eligible | Capitalizable
POLAR.4.1 | Unopened | POLAR.4.1 | Technical Documentation | 09/25/2012 8:00:00 AM | 10/02/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.4.1 | Technical Documentation | Unopened | 20120925 | 20121002 | Non Billable | R and D Eligible | Capitalizable
POLAR.4 | Unopened | POLAR.4 | Documentation | 09/25/2012 8:00:00 AM | 11/08/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.4 | Documentation | Unopened | 20120925 | 20121108 | Billable | R and D Eligible | Capitalizable
POLAR.3 | Unopened | POLAR.3 | Review Design | 08/22/2012 8:00:00 AM | 08/30/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.3 | Review Design | Unopened | 20120822 | 20120830 | Non Billable | R and D Eligible | Capitalizable
POLAR.2.3 | Unopened | POLAR.2.3 | Create Reports | 09/05/2012 8:00:00 AM | 09/25/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.2.3 | Create Reports | Unopened | 20120905 | 20120925 | Non Billable | R and D Eligible | Capitalizable
POLAR.2.2 | Unopened | POLAR.2.2 | Code Interface structure | 09/05/2012 8:00:00 AM | 09/19/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.2.2 | Code Interface structure | Unopened | 20120905 | 20120919 | Non Billable | R and D Eligible | Capitalizable
POLAR.2.1 | Unopened | POLAR.2.1 | Code security structure | 08/22/2012 8:00:00 AM | 09/05/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.2.1 | Code security structure | Unopened | 20120822 | 20120905 | Non Billable | R and D Eligible | Capitalizable
POLAR.2 | Unopened | POLAR.2 | Programming | 08/22/2012 8:00:00 AM | 09/25/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.2 | Programming | Unopened | 20120822 | 20120925 | Billable | R and D Eligible | Capitalizable
POLAR.1.3 | Unopened | POLAR.1.3 | Design Security | 08/14/2012 8:00:00 AM | 08/22/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.1.3 | Design Security | Unopened | 20120814 | 20120822 | Non Billable | R and D Eligible | Capitalizable
POLAR.1.2 | Unopened | POLAR.1.2 | Design Reports | 07/23/2012 8:00:00 AM | 08/14/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.1.2 | Design Reports | Unopened | 20120723 | 20120814 | Billable | R and D Eligible | Capitalizable
POLAR.1.1 | Unopened | POLAR.1.1 | Design Interface | 07/16/2012 8:00:00 AM | 07/27/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.1.1 | Design Interface | Unopened | 20120716 | 20120727 | Billable | R and D Eligible | Capitalizable
POLAR.1 | Unopened | POLAR.1 | Design | 07/16/2012 8:00:00 AM | 08/22/2012 8:00:00 AM | GailR |  | Polar | Polar Technology project | POLAR.1 | Design | Unopened | 20120716 | 20120822 | Billable | R and D Eligible | Capitalizable
POLAR | Opened | POLAR | Polar Project | 07/16/2012 8:00:00 AM | ed//Open 8:00:00 AM | Billable |  | Polar | Polar Technology project | POLAR | Polar Project | Opened | 20120716 | 20120822 | Billable | R and D Eligible | Capitalizable

## TASKRSRC
task_id | TASK__status_code | rsrc_id | role_id | acct_id | rsrc_type | start_date | end_date | delete_record_flag
Activity ID | (*)Activity Status | Resource ID | Role ID | Cost Account ID | (*)Resource Type | (*)Start | (*)Finish | Delete This Row
POLAR.6 | 20121009 | Non Billable |  |  | Labor | Ca/pi/Non 8:00:00 AM | Ca/pi/Non 5:00:00 PM
POLAR.5 | 20120925 | Non Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.4.3 | 20121018 | Non Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.4.2 | 20121002 | Non Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.4.1 | 20120925 | Non Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.4 | 20120925 | Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.3 | 20120822 | Non Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.2.3 | 20120905 | Non Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.2.2 | 20120905 | Non Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.2.1 | 20120822 | Non Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.2 | 20120822 | Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.1.3 | 20120814 | Non Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.1.2 | 20120723 | Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.1.1 | 20120716 | Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR.1 | 20120716 | Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
POLAR | 20120716 | Billable |  |  | Labor | ta/li/Capi 8:00:00 AM | ta/li/Capi 5:00:00 PM
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!
#REF! | #REF! | #REF! |  |  | Labor | #REF! | #REF!

## RSRC
rsrc_short_name | rsrc_name | rsrc_type | unit_id | role_id | def_qty_per_hr
Resource ID | Resource Name | (*)Resource Type | Unit of Measure | (*)Role ID | Default Units / Time(h/d)
Non Billable | R and D Non Eligible | Labor

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Day ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=dd'-'mmm'-'yy CurrencyFormat=Dollar